## Planning 2024
IN HIS NAME AND WITH THE HELP OF HIS LAST HUJJAT (ATFS)
| PLANNING - 2024 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
CENSUS
1 | C form Data to be monitored on a monthly basis. | bar: Jan to Aug
2 | Monthly interim report to be printed in first week of every month. | bar: Jan; Apr
3 | Quarterly interim report to be printed in first week of every quarter. | bar: Jan; Apr
4 | Half Yearly interim report to be printed in first week after siz month
5 | Yearly census report to be submitted in respective classes.
NAZEMEEN
1 | One CM (Consultency Meeting of Teacher) to be held. | Jan: CM has been conducten on 10th Aug 2024 with Respected Maulana Abedi Saheb.; Jul: Target - Dec 2024
2 | Two Nazmeen Meetings to be held. | Jul: Need to be conduct in Aug 2024, (delayed and scheduled for 20th Oct 24 - Nazim Nizam Nama to be shared by Br.Ashiq - Br.Murtuza Will schedule with Nazim
3 | Nazims to be changed in 1 or 2 years. | Jan: AUH1 - Done
DS3 - Nazim change not required
DS5 - New Nazim appointed in Mar 24.
4 | Follow up of irregular students every Month | bar: Jan
5 | Students reports to teachers (Six Monthly report) | bar: Jan
6 | Six monthly evaluation of each brother on the basis of: | Jan: need share with Teacher this Aug 2024 1 st Week
| a) Performance in class | Jan: Not achieved
b) Conduction (Student Class Report to be shared with Teacher)
c) Working in committee
EXAMINATION
1 | Exam anticipation chart to be prepared | bar: Jan to Sep
2 | QP as per request (Google MCQ links to be shared) | bar: Jan to Sep
3 | Paper results to be declared within 15 days. | bar: Jan to Sep
4 | Master mark sheet to be updated. | bar: Jan to Sep
5 | Re-exam to be followed up. | Jan: NA; Feb: N/A; Mar: N/A; Jul: Y; Aug: Y; Sep: Y
LIBRARY
1 | Database of Email Addresses of all Sec Brs to be maintained. | Jan: requested Nazim to provide the detail on 12 Aug 2024
2 | Books to be introduced via drop box.(Teacher to be requested) | bar: Jan
3 | Book related to current Aqaed to be provided (Teacher to be requested) | bar: Jan
4 | Books reading to be monitored in the classes, Nazim to take record of no. of Library Pages read during the week. | bar: Jan
5 | Workshops to be arranged for all brothers to improve library reading.(Once in a year - Picnic) | bar: Jan
CLASS VISITS
1 | Class visits to be arranged at least twice in a year. | Jan: 1- AUH-1 done on 16th Aug 2024 (Online) by Sir Ali Husain Lakhani 2-DS3 - Done on 27-09-24 3- DS5 - Done on 8th Sep 2024 (Online)
Y - Yes
N- No
W - Waiting
NA - Not Applicable
NAC- Not achieved

## 1H_CM_MOM
Date | 2024-08-10
Location | Br.Ashiq Residence
Time | 11:45 AM – 3:15 PM
Agenda | 1st Half Yearly CM (Consultency Meeting of Teacher)
# | Attendee
1 | Res. Maulana Abedi Saheb
2 | Res. Br.Firoz (Teacher)
3 | Res. Br.Mohd Raza Marchant (Teacher)
4 | Res Br.Zaheer Abbas (Teacher)
5 | Ashiq (Comm)
6 | Br.Naiyar Rizvi (Comm)
Area | Description
Motovation | Motivate Student with Gift
Liberary | Do not send complete book pdf, rather scan 2-3 pages topic wise and send in whatsapp.
NOTE: After 2-3 week delete all chats
The above task need to be done by teacher
Irregular Student | do not send in any other class, keep in same class