## Planning 2024
IN HIS NAME AND WITH THE HELP OF HIS LAST HUJJAT (ATFS)
| PLANNING - 2024 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
CENSUS
1 | C form Data to be monitored on a monthly basis. | bar: Jan to Dec
2 | Monthly interim report to be printed in first week of every Month. | bar: Jan; Apr; Jul to Dec
3 | 6 monthly census report to be submitted in respective classes. | Jan: Y; Jul: Scheduled In January
NAZEMEEN
1 | One CM (Consultency Meeting of Teacher) to be held. | Jan: CM has been conducten on 10th Aug 2024 with Respected Maulana Abedi Saheb.; Jul: Next Schedule is jan 2025 (Picnic) January 3rd Week (Proposed 19th jan 2025)
2 | Two Nazmeen Meetings to be held. | Jan: Need to be conduct in Aug 2024 (Date ???); Jul: Completed on 20th Oct 2024 Next Schedule is in March 2025
3 | Nazims to be changed once a year. | Jan: AUH1 -Done DS3 - N/A DS5 - N/A
4 | Follow up of irregular students every Month (attendance less than 75%) | bar: Jul to Nov
5 | Forward list of irregular students to teachers (Six Monthly IR report) | Jan: Y; Jul: Schedue in Dec 3rd Week
6 | Six monthly evaluation of each brother on the basis of: | Jan: need share with Teacher this Aug 2024 1 st Week
| a) Performance in class - Student Performance Report | Jan: N/A; Jul: Schedue in Dec 3rd Week
| b) Conduction of class (Student (Those who are taking class) Class Report) to be sent to Teacher | Jan: N/A; Jul: Schedue in Dec 3rd Week
| c) Working in committee | Jan: N/A; Jul: Schedue in Dec 3rd Week
EXAMINATION
1 | Exam anticipation chart to be prepared | bar: Jan to Dec
2 | QP to be supplied as per request (Few MCQ paper is ready that need to be supply) | bar: Jan to Dec
3 | Papers to be corrected within 15 days of receiving and result to be declared with prize. | bar: Jan to Dec
4 | Master mark sheet to be updated. | bar: Jan to Dec
5 | Re-exam to be followed up. | NA | N/A | N/A | Y | Y | Y | Y | Y | Y | Y | Y | Y
LIBRARY
1 | Database of Email Addresses of all Sec Brs to be maintained. | Jan: requested Nazim to provide the detail on 12 Aug 2024
2 | New books to be introduced via drop box.(Teacher to be requested) | bar: Jan
3 | Specific books relating to current Aqaed in classes to be provided to Brs. ((Teacher to be requested)) | bar: Jan
4 | Books reading to be monitored in the classes, Nazim to take record of no. of Library Pages read during the week. | bar: Jan
5 | Workshops to be arranged for all brothers to improve library reading.(Once in a year - Picnic) | bar: Jan
CLASS VISITS
1 | Class visits to be arranged at least twice in a year. | Jan: 1- AUH-1 done on 16th Aug 2024 (Online) by Sir Ali Husain Lakhani 2-DS3 - Done on 27-Sep-2024 3- DS5 - Done on 8th Sep 2024 (Online); Jul: Next Planned in March 2025
Y - Yes
N- No
W - Waiting
NA - Not Applicable

## 1H_CM_MOM
Date | 2024-08-10
Location | Br.Ashiq Residence
Time | 11:45 AM – 3:15 PM
Agenda | 1st Half Yearly CM (Consultency Meeting of Teacher)
# | Attendee
1 | Res. Maulana Abedi Saheb
2 | Res. Br.Firoz (Teacher)
3 | Res. Br.Mohd Raza Marchant (Teacher)
4 | Res Br.Zaheer Abbas (Teacher)
5 | Ashiq (Comm)
6 | Br.Naiyar Rizvi (Comm)
Area | Description
Motovation | Motivate Student with Gift
Liberary | Do not send complete book pdf, rather scan 2-3 pages topic wise and send in whatsapp.
NOTE: After 2-3 week delete all chats
The above task need to be done by teacher
Irregular Student | do not send in any other class, keep in same class